## Sheet1
Phases | Start Date | End Date | Duration
Phase 1 | 2023-02-15 | 2023-03-06 | 19
Phase 2 | 2023-03-07 | 2023-04-09 | 33
Phase 3 | 2023-04-10 | 2023-04-29 | 19
Phase 4 | 2023-04-30 | 2023-05-16 | 17
Phase 5 | 2023-02-08 | 2023-05-16 | 98
|  |  |  | Phase 1 | Project scope, Planning and Task Definition
|  |  |  | Phase 2 | Literature Review
|  |  |  | Phase 3 | Preliminary Design
|  |  |  | Phase 4 | Detailed System Design/Technical Details
|  |  |  | Phase 5 | Work Ethics
Designed By- Darshan